# The Workflow & Process of Data Migration for BRAC Payroll Management System

## 1. Introduction

This documentation provides an end-to-end overview of the data migration process for the BRAC Payroll Management System. The primary goal is to consolidate data from multiple source systems (PostgreSQL, MSSQL Server, MySQL) into one destination PostgreSQL server. This migration is executed in a phased approach, focusing on Master Data, Employee Data, and Leave & Attendance Data. It outlines the workflow, key responsibilities, dependencies, and management steps involved.

## 2. Objectives

- Objective:
To transform and migrate data from multiple source databases into a unified PostgreSQL environment that supports the Payroll Management System.

- Module:

  - Phase 1: Leave & Attendance Module (divided into three parts)

    - Master Data Migration

    - Employee Data Migration

    - Leave & Attendance Data Migration

- Source Systems:

  - ERP Data: Sourced from a PostgreSQL database.

  - Leave Tools Data: Sourced via dump/restore from a MySQL database.

  - Attendance Data: Extracted from an MSSQL Server using an ETL pipeline built with Airflow, Airbyte, Python, and SQL.

  - Manual Data from BRAC: Collected data in Excel format.

## 3. Workflow Overview

The migration is divided into several major steps:

- Data Sourcing & Extraction:

  - Data is sourced from various source systems.

  - Creation of staging tables within dedicated schemas in a VM:

    - payroll_master_data

    - payroll_emp_data

    - payroll_leave_attend_data

  - Each schema holds staging tables corresponding to the three migration steps.

- Backup & Restore to Destination Server:

  - Once staging tables are populated, the schemas are backed up.

  - The backup is restored onto the destination PostgreSQL server (Inteacc's Postgres Instance) by the DevOps & Infra Team.

- Data Transformation & Interim Loading:

  - SQL scripting is used to transform data according to scope, span, and business rule requirements.

  - Data from the staging schemas is transformed and loaded into interim tables in the public (main) schema on the destination server.

- Final Data Load:

  - Inteacc transfers data from the interim tables to the respective main tables of the Payroll Management System software.

## 4. Detailed Process Steps

### Step 1: Data Sourcing & Extraction

- Activities:

  - Extract Data from ERP:

    - Connect to the source PostgreSQL ERP.

    - Extract respective data as per requirement.

    - Load the data into corresponding staging tables into the respective schema of the VM.

  - Extract Data from Leave Tools:

    - Dump data from the MySQL-based Leave Tools.

    - Restore the data into staging tables into the respective schema of the VM.

  - Extract Data from Attendance System:

    - Use the ETL pipeline (Airflow, Airbyte, Python, SQL) to extract attendance data from the SQL Server.

    - Load the data into corresponding staging tables into the respective schema of the VM.

- Responsibilities:

  - Data Team:

    - Design and implement extraction queries and ETL pipelines.

    - Validate data quality during extraction.

  - Source System Owners:

    - Ensure availability and performance of source databases during extraction.

### Step 2: Backup & Restore to Destination Server

- Activities:

  - Backup the three dedicated schemas (payroll_master_data, payroll_emp_data, payroll_leave_attend_data) containing the staging tables.

  - Restore the backups to the destination PostgreSQL server (Inteacc's instance).

- Responsibilities:

  - DevOps & Infra Team:

    - Manage the backup process from the source VM.

    - Ensure secure and reliable restoration on the destination server.

  - Data Team:

    - Confirm the integrity and completeness of the restored data.

### Step 3: Data Transformation & Interim Loading

- Activities:

  - Develop SQL scripts to perform data transformation:

    - Scope-Based Transformation:
Transform data to meet business requirements and the defined scope.

    - Span & Business Rule Transformation:
Apply necessary business rules to map and cleanse the data.

  - Load the transformed data into interim tables within the public schema.

- Responsibilities:

  - Data Team:

    - Write, Analyse, and execute SQL transformation scripts.

    - Ensure that the transformation logic adheres to business rules.

  - Quality Assurance:

    - Validate that the transformed data matches the source data in context and quality.

### Step 4: Final Data Load to Main Payroll System Tables

- Activities:

  - Transfer data from the interim tables in the public schema to the final, production-ready main tables of the Payroll Management System.

  - Perform post-migration validations and data integrity checks.

- Responsibilities:

  - Inteacc Team:

    - Oversee the final data loading process into the Payroll Management System.

    - Validate that all migrated data supports operational needs.

## 5. Dependency Flow

The data migration process involves a dependency workflow among the various teams:

- Initial Master Configuration Load:

  - The Data Team and the HRM Team collaborate to gather and scriptualize all the Master Configuration data into a SQL script.

  - This script is executed in the provided blank database on the destination PostgreSQL server (Inteacc's instance) by both the Data Team and the HRM Team, populating the respective Main tables.

  - Once the Master Configuration data is successfully inserted, the subsequent migration steps can proceed.

- Master Data Migration:

  - The Data Team sources, accumulates, finalizes, and populates staging tables in the payroll_master_data schema using various techniques mentioned above.

  - The DevOps & Infra Team then backs up and restores this schema to the destination PostgreSQL server (Inteacc's Postgres instance).

  - Next, the Data Team migrates the Master Data into the interim tables via SQL scripting.

  - Finally, the Inteacc team processes the interim Master Data and transfers it into the Main Tables.

- Employee Data Migration:

  - After the Master Data processing is complete, the Data Team proceeds with the Employee Data.

  - Similar to the Master Data process, the staging tables for Employee Data are populated.

  - The DevOps & Infra Team backs up and restores the corresponding schema.

  - The Data Team then migrates the Employee Data into interim tables.

  - The Inteacc team processes this data and transfers it into the Main Tables.

- Leave & Attendance Data Migration:

  - Following the Employee Data processing, the Data Team works on the Leave & Attendance data.

  - Data is sourced and staged in the respective schema.

  - The DevOps & Infra Team backs up and restores this schema.

  - The Data Team migrates the data into interim tables.

  - Finally, the Inteacc team processes the data and transfers it into the respective Main Tables.

Key Note:
Each party (Data Team, HRM Team, DevOps & Infra, and Inteacc) operates on their own timeline and takes the necessary time to complete their tasks. This dependency flow ensures that data migration proceeds in a sequential manner, with each phase relying on the successful completion of the previous step.

## 6. Conclusion

The migration of the Leave & Attendance module in the BRAC Payroll Management System is a complex, multi-step process requiring close collaboration between various teams. By clearly defining the responsibilities, dependencies, and transformation processes, this documentation aims to serve as a guide to ensure a smooth and successful migration.